Rise Together: Pathways for Newcomer Women

Sahan Heritage Foundation  ·  Calgary, Alberta

CIP Project Grant — Project Plan & Budget Summary (full cash-match, lean in-kind)

Project Snapshot

| Applicant organization | Sahan Heritage Foundation |
| --- | --- |
| Location | Calgary, Alberta |
| Program | Rise Together: Pathways for Newcomer Women |
| Model | 1 cohort · 15 women · 12 weekly Saturdays (60 contact hours) |
| Venue | Donated — Somali Canadian Society hall (in-kind, with letter) |
| CIP request | $24,000 |
| Sahan cash committed | $17,000 — full co-investment (≈$0 reserve retained) |
| Matching contribution | $32,960 (cash $17,000 + in-kind $15,960) = 137% of request |
| Total project cost | $56,960 (CIP share 42.1%, under the 50% cap) |
| Match composition | 52% cash / 48% in-kind |
| Direct beneficiaries | 15 women + ~15–25 children + 4 mentors + 5–8 partner-community participants |
| Delivery window | [Project start date] – [end date], within 18 months of grant payment |

About the Applicant

Sahan Heritage Foundation is a community-led non-profit serving East African and Black newcomer families in Calgary. Sahan is a sister society to Horn Youth Services Foundation (operating as KULAN) in Edmonton, which designed and delivered Rise Together for newcomer women.

Building on KULAN's model and lessons learned, Sahan will deliver a single, strong Calgary cohort tailored to local participants, venues, and partners. The proposal is scoped to one well-resourced 12-week cohort and backed by a substantial cash co-investment from Sahan, signalling organizational commitment and capacity to deliver.

Community Need

Across Calgary's East African and Black communities, many newcomer women face overlapping barriers to economic participation: limited English fluency, no Canadian work history, and — most decisively — a lack of childcare that puts existing employment and settlement services out of reach. In many families, women carry full responsibility for the home and children without the extended-family support they relied on in their countries of origin. As a result, they miss the very programs designed to help them: language training, employment assistance, and job-readiness seminars.

Sahan identified this need the way it knows its community best — through door-to-door and phone outreach, informal conversations, and direct feedback from women who repeatedly said they could not attend programming that did not also care for their children. Rise Together is built around removing that barrier: free, registered, on-site childcare runs the full program day so mothers can fully participate.

Target Population

Newcomer women in Calgary, primarily from East African and Black communities

Women who do not yet speak English fluently

Single mothers who are unemployed or under-employed

Women who have lived in Canada for years but have never entered the Canadian workforce (e.g., raised children at home or were caregivers)

Program Design

Format: 15 women per cohort, one Saturday per week for 12 consecutive weeks — 5 contact hours per Saturday, 60 hours total.

Weekly schedule:

| Time | Activity | Length |
| --- | --- | --- |
| 9:45–10:00 am | Arrival, sign-in, children to babysitters | 15 min |
| 10:00 am–1:00 pm | Session 1 — Job Readiness Workshop | 3 hrs |
| 1:00–2:00 pm | Hot lunch (women + children together) | 1 hr |
| 2:00–4:00 pm | Session 2 — Conversational English + Mentor Time | 2 hrs |
| 4:00–4:15 pm | Pickup, weekly handout, debrief | 15 min |

Session 1 — Job Readiness (rotating themes):

Weeks 1–2: Self-assessment, transferable skills, Canadian workplace introduction

Weeks 3–4: Resume building with ESL-adapted templates

Weeks 5–6: Cover letters, online job applications, job-board navigation

Weeks 7–8: Interview preparation and mock interviews with feedback

Weeks 9–10: Workplace communication — phone, professional email, workplace norms

Weeks 11–12: Networking, mentor matching, individual next-steps planning

Session 2 — Conversational English + Mentorship:

First hour: workplace-vocabulary ESL tied to that week's morning topic

Second hour: small-group mentor circles (3–4 women per mentor)

Employment & Digital Supports

Backed by Sahan's cash co-investment, this cohort adds dedicated employment and digital supports beyond the core sessions:

One-on-one employment coach: a contracted coach provides individual resume, application, and interview support to each participant.

Digital-literacy laptops: six shared laptops/tablets let participants practise online job searches, applications, and email — many for the first time.

Graduation celebration (Week 12): a closing event with certificates to mark completion and reinforce community.

Children's Room

A separate room at the venue staffed the full program day (9:45 am–4:15 pm)

Three registered / certified babysitters on-site all day (sized for up to ~25 children)

Mixed ages infant to ~age 10; play mats, age-grouped stations, nap and snack areas

Sign-in/out logs for every child each Saturday (safety and insurance requirement)

Children eat lunch with their mothers at 1 pm; all food halal-only with a vegetarian option

Food Provided Every Saturday

| Time | Meal | Notes |
| --- | --- | --- |
| 10:00 am | Morning snack | Fruit, pastries, tea, coffee, water |
| 1:00–2:00 pm | Hot lunch | Culturally familiar rotating menu; women + children together |
| 2:30 pm | Afternoon snack | Fruit, juice, small treat for children |

All food is halal-only with a vegetarian option every week.

Staffing Per Saturday

| Role | # | Notes |
| --- | --- | --- |
| Lead Facilitator (Job Readiness) | 1 | HR/employment background; culturally competent (contract) |
| Employment / Job-Search Coach | 1 | 1:1 resume & interview coaching (contract) |
| ESL Instructor | 1 | TESL-certified; Session 2 (contract) |
| Registered Babysitters | 3 | Full day in the children's room |
| Program Coordinator | 1 | Intake, logistics, food and mentor coordination (part-time contract) |
| Volunteer Support | 1–2 | Setup, food service, sign-in |
| Mentors (rotating) | 3–4 | Session 2, paired with small groups |

Venue & Partnerships

Venue (donated): The program will run at the Somali Canadian Society hall in Calgary, provided free of charge for all 12 program Saturdays. Because the Society is a separate organization donating the use of its space, this contribution is claimed as in-kind match at fair market value (approximately $9,000 for the 12 program days). The Society will provide a letter on its letterhead confirming the donated dates and the rental value; this letter also serves as the venue titleholder's letter of support.

Bridges partner: A separate cross-community partner — [Partner organization — confirm name] — joins the Week 8 Bridges event, bringing 5–8 women from another Calgary cultural or faith community.

Bridges Cross-Community Event

Around Week 8, the standard Session 2 is replaced with a joint cooking, storytelling, and skill-share circle bringing together participants and a small delegation (5–8 women) from the partner organization. It builds tolerance, anti-racism, and social inclusion; gives participants direct exposure to working women from another community; and demonstrates a genuine cross-cultural partnership to the funder. Same venue, same childcare, lunch extended to include both groups.

Materials Each Participant Receives

ESL-adapted workbook used in both sessions

Resume and cover-letter templates (printed and digital)

Access to a shared program laptop/tablet for job-search and digital-literacy practice

Bus pass valid for the 12 weeks of the program

Mentor introduction packet (Week 6)

Certificate of completion (Week 12)

Outcomes & Measures

| Measure | Target |
| --- | --- |
| Women completing the 12-week cohort | 13 of 15 |
| Women with a finalized resume by program end | 15 of 15 |
| Women completing at least one mock interview | 13 of 15 |
| Women applying to at least one job by program end | 10 of 15 |
| Mentor relationships established | 15 |
| Children safely cared for across the cohort | 15–25 |
| Attendance rate per participant | ≥ 75% |
| Confidence in workplace English | Pre/post survey gain |
| Bridges event participation | 5–8 partner-community guests + reflection |

Budget Summary & Matching Plan

| CIP request | $24,000 |
| --- | --- |
| Sahan cash match | $17,000 (full co-investment) |
| In-kind match | $15,960 (donated venue + mentor & volunteer hours) |
| Total matching | $32,960 (137% of request) |
| Total project cost | $56,960 |
| CIP share of total | 42.1% (under the 50% cap) |
| Match composition | 52% cash / 48% in-kind |

Sahan commits its full $17,000 in cash to the project, funding enhancements such as the employment coach, digital-literacy laptops, the third babysitter, the graduation event, and richer catering and transit. In-kind is kept lean and defensible — the donated venue plus mentor and program-day volunteer hours ($15,960) — bringing matching to $32,960, or 137% of the request, with CIP's share at 42.1% of total cost. CIP requires the match to be at least 100% of the ask; because the $17,000 cash already covers most of it, only about $7,000 of in-kind is strictly required (the donated hall alone would meet it). The mentor and volunteer hours are retained as a buffer in case the hall is valued below fair market value. The match is now 52% cash, a strong signal of organizational commitment. Facilitators and the coordinator are engaged as contractors, so the program avoids the requirement that new staff wages be matched with cash. Full line-item detail is in the accompanying budget spreadsheet.

Important — no cash reserve: committing the full $17,000 leaves Sahan with essentially no cash cushion during the project. Confirm the organization can meet its operating costs from other income over the delivery period; CIP does not require an applicant to commit its entire reserve. The donated-venue claim also depends on documentation — confirm that CIP values donated facility space at fair market value, not a standardized hourly rate.

Why This Project Fits CIP

New initiative in Calgary — not an ongoing or status-quo program

Substantial cash co-investment (52% of the match) signals organizational commitment

Gender equity — women-only, addressing domestic-labour and isolation barriers

Newcomer integration and employment outcomes (resumes, interviews, workplace English, digital literacy)

Social inclusion and anti-racism through the cross-community Bridges component

Serves multiple equity-deserving groups: newcomers, women, racialized and low-income people, and children

Addresses a real, documented barrier — childcare is the reason many single mothers miss existing programs

Registered/certified childcare signals professional duty of care, not informal minding

Before You Submit — Confirm These

Reserve: committing the full $17,000 leaves no cash cushion — confirm Sahan can meet operating costs from other income during the project.

Venue letter: obtain the Somali Canadian Society letter on letterhead, listing all 12 program dates and stating the donated rental value (~$9,000); it doubles as the venue titleholder letter of support.

In-kind valuation: confirm with Community Grants that donated facility space is valued at fair market value; if only a standardized rate applies, adjust the in-kind figure.

Eligible applicant: confirm Sahan Heritage Foundation's registration type and that it has operated ≥ 1 year with an active Alberta address.

Mission/mandate: insert Sahan's own registered mission — do not reuse KULAN's wording.

Bridges partner: name the Calgary cross-community partner and obtain a letter of support.

Quotes: obtain written estimates for laptops/technology, catering, transit, and materials.

In-kind letters: collect letters on company letterhead for mentors, volunteers, the Bridges partner, and donated goods.

Keep staff as contractors: avoids the cash-match-for-wages requirement.