# Warm Homes, Warm Welcome — MASTER PROJECT PLAN

## Sahan Heritage Foundation | 3 Sessions + Competition Finale, January–February 2027

Companion document: `enmax-sponsorship-submission-warm-homes-warm-welcome.md` (same folder) Plan created: September 3, 2026 Key dates: ENMAX meeting ~Sept 8–10, 2026 | Sessions start January 15, 2027

## 0. The Why — What This Project Is and Why It Matters

Use this section, in your own voice, in the conversation with Adam.

Every year, families arrive in Calgary in November with nothing that prepares them for a

Canadian winter — no experience with minus-thirty windchill, no understanding of an Alberta

utility bill, no idea what a carbon monoxide alarm sounds like, and no one to ask.

Sahan Heritage Foundation exists for exactly these families. We are a volunteer-run,

registered Alberta society serving about 1,300 newcomers a year. And what our volunteers

keep seeing, over and over, is the same winter story: a family gets their first utility

bill and cannot tell what they're paying for. They blast the heat to 26 degrees because

nobody told them 20 is enough — or the safe one. They have never heard that they can

choose a retailer, or that 211 exists, or that ENMAX has payment support when things

get tight.

Warm Homes, Warm Welcome turns that first dangerous, confusing winter into a welcome.

Three free evening sessions — dinner shared, guides in their own language, every family

leaving with a winter efficiency kit they can use that same night. Then the learning

locks in through the Warm Homes Challenge: a live family-versus-family game where they

have to apply what they learned — read a mock bill, make the cost comparison, sort the

recycling, and explain the reasoning out loud. People remember what they had to stand

up and defend in front of their neighbours. That's the design.

Why it should matter to ENMAX specifically:

this is your Energy Efficient Futures model — community energy education — delivered to

the audience that model currently doesn't reach: brand-new Calgarians who will be ENMAX

customers within their first year. Better-informed customers make better rate choices,

heat safely, and call for payment help before they're in collections. The financial

case and the human case point the same direction.

What we are asking is small on purpose — $1,500, everything else donated — because

this is our first corporate partnership and we intend to deliver it flawlessly, measure

it honestly, and report back with photos, attendance, and before-and-after knowledge

results. If it works — and it will — it becomes a repeatable winter program, and ENMAX

was there first.

The ask: $1,500 for meals, translated guides, and efficiency kits · an ENMAX speaker

if one is willing · recognition on all materials and in our final report.

### Goals snapshot

| Goal | How we'll know |
| --- | --- |
| 30 newcomer families attend, most attending 2+ sessions | Registration + attendance sheets |
| Families can read a bill and choose a rate confidently | Pre/post knowledge check (+challenge performance) |
| Every family applies at least one efficiency measure at home | Kit distribution + event-night demo |
| Families know where to get help (211, ENMAX support) | Post-quiz + challenge Round 3 answers |
| Zero winter safety gaps among attendees | CO/frozen-pipe safety covered, CO knowledge in quiz |
| A repeatable, funder-ready winter program exists | Documented curriculum, budget actuals, final report |

## Phase 0 — Now (September 2026): Secure the Money

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 0.1 | Video meeting with Adam Tomasta (ENMAX Energy Education team) | Director | Sept 8 or 10 | Bring prep points; ask about speaker, neutral-content framing, in-kind support |
| 0.2 | Send thank-you email same day, summarizing what was discussed | Director | Day of meeting | Creates a paper trail of any verbal commitments |
| 0.3 | Record outcome (funded / partial / in-kind / declined + amount) | Director | When received | Update section 1 of the submission record |
| 0.4 | If declined or partial: trigger fallback (see §10 Contingency) | Director | Same week | Servus / ATCO / AltaGas pipeline |

Decision gate: you cannot lock food, kits, or printing until at least one funder is confirmed.

## Phase 1 — October 2026: Lock the Foundations

### Funding pipeline

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 1.1 | Submit Servus Feel Good Fund application (adapted ENMAX pitch, "Community Access" frame) | Director | Early Oct | Hard requirement: apply ≥3 months before Jan sessions |
| 1.2 | Submit Good Places Grant ("Friday Welcome Nights") — cites ENMAX support if confirmed | Director | Oct 20 | See `sahan-friday-welcome-nights-good-places-grant.md` |
| 1.3 | Open a dedicated budget tracking sheet for this project; ENMAX money stays 100% separate from Good Places lines | Treasurer | Before first expense | No double-funding rule from the application |

### Venue

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 1.4 | Confirm 3 dates with Somali Canadian Society of Calgary; get dates in writing | Director | Mid Oct | Sessions are 2 hrs + setup/cleanup → book 4 hr blocks |
| 1.5 | Refresh / obtain the in-kind letter naming the venue and dates | Venuve contact | Mid Oct | Needed for funder reporting |
| 1.6 | Site visit: check kitchen/warming capacity, tables/chairs for 30–40, projector or screen, mic, accessibility, parking/transit access | 2 volunteers | Late Oct | Photograph the space |

### Team

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 1.7 | Recruit 6–8 session volunteers (2 content leads, 2 registration/welcome, 2 food/kits, 1 interpreter floater) | Volunteer coord | Late Oct | Prioritize bilingual Somali/English |
| 1.8 | Schedule volunteer training night (covers curriculum, neutrality rules, safety talking points) | Director | Early Dec | 2 hours |

## Phase 2 — November 2026: Build the Content & Registration

### Curriculum

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 2.1 | Finalize Session 1 content: sample bill walk-through, retailer vs. Regulated Rate, all sourced from ucahelps.alberta.ca | Content leads | Mid Nov | Neutral — no steering toward any retailer |
| 2.2 | Finalize Session 2 content: heating safety, CO detectors, frozen pipes, draft-proofing, thermostat habits | Content leads | Mid Nov | Bring physical demo items (weatherstripping, film kit, CO alarm) |
| 2.3 | Finalize Session 3 content: 211 Alberta, ENMAX payment support, affordability programs, Q&A | Content leads | Mid Nov | Confirm current program names/phone numbers that month |
| 2.4 | Build the take-home "Winter Guide" (~4 pages, plain language, visuals) | Director + designer | Late Nov | ENMAX logo/recognition added per sponsorship agreement |
| 2.5 | Translate guide into Somali + 1–2 additional languages | Translators | Late Nov | Prioritize by registration data if known |
| 2.6 | Design pre/post knowledge check (5–6 questions, paper, translated) | Content leads | Late Nov | Same questions before & after each session |

### Registration & promotion

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 2.7 | Set up free registration (Google Form or Eventbrite free tier) capturing: name, language, family size, dietary needs, which sessions | Director | Early Nov | Cap ~40 per session |
| 2.8 | Create simple poster (bilingual) + WhatsApp/Facebook posts | Volunteer | Early Nov | Distribute through Sahan channels, SCSC, newcomer agencies |
| 2.9 | Register promotion through partner agencies (immigrant-serving orgs, mosque/community groups) | Director | Mid Nov | Ask partners to forward, not just post |

### Procurement

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 2.10 | Get 2–3 catering quotes for 3 dinners (~40 portions each, halal) | Food volunteer | Late Nov | Confirm dietary options |
| 2.11 | Price winter efficiency kits: weatherstripping, window film, LED bulb, CO safety checklist — 30 kits @ ≤$10 | Kits volunteer | Late Nov | Check Dollarama/hardware bulk vs. Home Depot bulk |
| 2.12 | Get printing quote for guides (3 language versions × ~40 each) | Director | Late Nov | Confirm sponsorship logo usage rights first |

## Phase 3 — December 2026: Lock Everything

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 3.1 | Confirm catering order with delivery timing per session | Food volunteer | Early Dec | Give final headcount 5 days before each session |
| 3.2 | Assemble 30 winter kits (team packing night — good volunteer photo op) | Volunteers | Mid Dec | Bag, contents photo for report |
| 3.3 | Send guides to print | Director | Early Dec | Allow 2-week turnaround buffer |
| 3.4 | Run volunteer training night | Director | Early Dec | Include neutrality rule: no steering to any retailer, ENMAX branding is thanks-not-endorsement |
| 3.5 | Print registration lists, pre/post quizzes, sign-in sheets, photo consent forms | Director | 1 week before S1 | Photo consent required for anyone in report photos |
| 3.6 | Reminder message to all registrants (WhatsApp/SMS/email) — 1 week + 2 days before each session | Volunteer coord | Per session | Biggest attendance lever |
| 3.7 | Build the Warm Homes Challenge host kit: 20-question bank with correct answers + explanations, score flip-chart, spoon buzzers, mystery-bin props, cart props, prize packs, certificates | Director + host | Early Jan | Verify Bin It Right answers against City of Calgary What Goes Where that week |
| 3.8 | Rehearse the challenge once with volunteers as mock teams | Host | ~Jan 8 (dry run) | Host pacing, buzzer mechanics, explanation prompts |
| 3.9 | Full dry run at venue (1 hr) with content leads | Team | ~Jan 8 | Test projector, food warming, room layout |

## Phase 4 — Session Days (Jan 15, ~Jan 29, ~Feb 12, 2027)

### Run of show (2-hour session, doors 30 min early)

| Time | Activity | Who |
| --- | --- | --- |
| T−2:00 | Setup: tables, food warmers, registration desk, kit stack, bins + mystery-bin props staged, projector test, signage | Setup crew |
| T−0:30 | Doors open — registration, name tags, pre-quiz (5 min, paper). Families eat; volunteers sit with them | 2 volunteers |
| T+0:00 | Welcome, photo-consent reminder, thank sponsors (ENMAX named). Set the night's promise: "leave knowing 3 things + supplies for tonight" | Director + all |
| T+0:10 | Dinner continues with informal table chat (trust-building) | All volunteers |
| T+0:30 | Main content block (40 min, interactive, hands-on demos) | Content lead + interpreter |
| T+1:10 | Warm Homes Challenge — 25 min live competition (see §4B) | Host + 2 teams |
| T+1:35 | Kit distribution by table — challenge winners collect first; 30-second kit demo at the stack | Kits volunteer |
| T+1:45 | Post-quiz; where-to-get-help recap; ENMAX speaker Q&A if attending (Session 3, safety/billing only — no marketing) | Content lead |
| T+1:55 | Closing: next session date, WhatsApp reminder, funder thank-you slide | Director |
| T+2:00 | Cleanup, pack leftover food for families if safe, debrief 15 min | All |

### Why the evening is built this way

• Eat first, teach second — dinner is the attendance mechanism; hungry parents learn nothing.

• Everything hands-on — touching the CO alarm and applying weatherstripping beats any slide.

• Competition replaces passive recap — families have to apply what they heard, out loud, in

front of neighbours. That is where the learning locks in.

• The kit leaves in their hands the same night — "make your home warmer tonight" is the whole program promise.

### 4B. The Warm Homes Challenge — Full Competition Design

Format. Gameshow-style up front: 2 teams × 3 adults (drawn from different families),

standing at a table on each side of the host. Audience plays along on paper cards so nobody

is just watching. ~25 minutes: 3 rounds × 5 questions + bonus round.

Why it works. Newcomer adults often won't raise a hand to ask "dumb" questions in a lecture —

but they'll shout an answer for their team. Competition converts embarrassment into energy, and

every answer must be explained, which is where the teaching actually lands. It also generates

footage and scores we can put in the ENMAX report as evidence of learning.

Mechanics.

• Host reads question → first team to buzz (wooden spoon on table — loud, funny, free) answers

• Correct = 10 pts; wrong = opposing team steals for 5

• Bonus round answers require an explanation, not just the answer

• Each team gets one "ask the room" lifeline per match

• Prizes: premium LED bulb + CO alarm combo (~$15/team) + printed "Warm Homes Champion"

certificate. Everyone still gets the standard winter kit — no family leaves empty-handed.

Absorbed inside the $300 kits line (~$30 total).

#### Round 1 — The Money Round (bill understanding)

Every question forces a dollar comparison between two practices — families must reason about

real financial differences:

• "Family A heats to 22°C all winter; Family B heats to 20°C and 17°C overnight. Who pays less, and roughly how much?" (≈5% saved per degree lowered)

• "Farah's bill: $180 energy + $95 delivery/fees. Ahmed's: $140 energy + $95 delivery/fees. Ahmed used less energy — why did his total bill barely drop?" (fixed delivery charges — the most-misunderstood line on any Alberta bill)

• "Two identical homes, identical usage. One family on a fixed-rate plan, one on the Regulated Rate. Name one risk each family takes."

• "Does running your dryer at noon instead of 9 PM change your Calgary bill? Why or why not?"

• "Which costs a family more over one winter: heating a spare room nobody uses, or leaving a second fridge running in the garage?"

#### Round 2 — Winter-Proofing Round

• "Your CO alarm beeps 4 times then pauses. What do you do in the next 60 seconds?"

• "Which saves more over one winter: a window film kit or one LED bulb? Explain."

• "Your pipes freeze while you're away two weeks. Name the one habit that prevents this."

• "True/false: a space heater next to curtains is fine if you watch it."

• "Where in the home should a CO alarm go — and why not right beside the furnace?"

#### Round 3 — Bin It Right (waste management)

Physical prop round — the crowd-pleaser. The host tips a "mystery bin" onto the table

(pizza box, plastic bag, foil tray, banana peel, old battery, chip bag) and teams race to sort

items into blue / black / green cart props, host judging against the City of Calgary

What Goes Where tool. Plus spoken questions:

• "Why does plastic film jam the recycling facility?"

• "Name two habits that shrink this family's black-cart volume in half."

*Note: waste content is new since the application — confirm with Adam whether the ENMAX speaker

is comfortable with this round, or run it as the audience warm-up round instead.*

#### Bonus Round — Plan the Month

Both teams get a scenario card: a newcomer family with $200 to spend on home efficiency.

Allocate it (thermostat habits, kit items, curtains, etc.) and present in 60 seconds. Host scores

on reasoning; room votes by applause. Doubles as the session's summary — every family watching

just heard the whole curriculum applied once more.

Host kit: question cards with correct answers + one-line explanations on the back, score

flip-chart, wooden-spoon buzzers ×2, mystery-bin props, cart props, prize packs, certificates.

### Per-session checklist (print one per date)

☐ Registration list + walk-in sheet + pens

☐ Name tags (write preferred language on it)

☐ Pre/post quizzes in all languages

☐ 40 take-home guides (language mix per registrations)

☐ 15 kits (only for families who registered — order of arrival)

☐ Photo consent forms

☐ Cash box / receipts envelope (all expenses receipted same day)

☐ First-aid kit, venue emergency contact, CO alarm demo unit

☐ Warm Homes Challenge kit: question cards, score flip-chart, spoon buzzers ×2, mystery-bin props, blue/black/green cart props, prize packs, "Champion" certificates

☐ Attendance count recorded before leaving

## Phase 5 — After the Series (Feb–Mar 2027)

| # | Task | Owner | Due | Notes |
| --- | --- | --- | --- | --- |
| 5.1 | Tally attendance + pre/post quiz results per session | Director | 1 week after S3 | This is your promised measurement |
| 5.2 | Write the report to ENMAX: numbers, photos (consented only), 2–3 family quotes, budget actuals | Director | 2 weeks after S3 | Promised in the application |
| 5.3 | Thank-you notes: ENMAX, venue (SCSC), caterer, volunteers, translators | Director | 2 weeks after S3 | Volunteers get reference letters on request |
| 5.4 | Debrief meeting: what worked, costs vs. budget, lessons | Team | 3 weeks after S3 | Feeds Servus/ATCO next applications |
| 5.5 | Update pipeline records with final outcomes | Director | 3 weeks after S3 | Close the loop on the submission record |

## 6. Budget Control (as submitted — track actuals against this)

| Line | Budget | Actual |
| --- | --- | --- |
| Warm meals, 3 sessions | $750 |  |
| Multilingual printed guides | $400 |  |
| Winter kits (30 × $10) | $300 |  |
| Venue | $0 (in-kind) |  |
| Total | $1,500 |  |

Rules: every expense gets a receipt same day; ENMAX-funded lines never touch Good Places budget; overspend needs Director + Treasurer sign-off before purchase.

## 7. Roles Roster (fill in)

| Role | Name | Phone/Email |
| --- | --- | --- |
| Director / ENMAX liaison | Abdikhadar Hassan Obsiye |  |
| Treasurer / budget |  |  |
| Venue contact (SCSC) |  |  |
| Content lead 1 (Session 1) |  |  |
| Content lead 2 (Session 2) |  |  |
| Content lead 3 (Session 3) |  |  |
| Registration & reminders |  |  |
| Food coordinator |  |  |
| Kits coordinator |  |  |
| Interpreter floater(s) |  |  |
| Translator(s) |  |  |

## 8. Risk List

| Risk | Mitigation |
| --- | --- |
| ENMAX declines / partial funds | Reduce scope (2 sessions or no printed guides — digital instead); accelerate Servus/ATCO/AltaGas |
| Low registration | Partner-agency push + personal WhatsApp invites; minimum viable audience is 15 families |
| Winter storm on session night | Cancellation rule: decide by noon day-of; WhatsApp blast; reschedule date reserved with venue in advance |
| No-show rate | Overregister 25%; two reminders per session |
| Kit costs exceed $10 | Swap window film for second LED bulb, or reduce kits to 2 core items + checklist |
| Funder content influence | Curriculum locked to ucahelps.alberta.ca materials; speaker agreement: safety/billing education only, no product pitches, no data collection |
| Language gaps | Name tags mark preferred language; interpreter floater roams during content blocks |

## 9. Communications Templates Needed (draft by Dec)

☐ Registration confirmation message

☐ Reminder message (T−7 days and T−2 days)

☐ ENMAX thank-you + reporting cover email

☐ Cancellation/weather message

☐ Speaker briefing note for ENMAX employee (role, boundaries, timing)

## 10. Contingency — If ENMAX Says No

1. Same week: submit ATCO + AltaGas versions (pitches are already ~90% written).

2. Trim plan to 2 sessions and digital-only guides → viable at ~$600, coverable from a Servus Feel Good Fund or internal funds.

3. Keep venue and volunteer commitments unchanged — scope, not cancellation.

4. Re-approach ENMAX for a future event (e.g., Friday Welcome Night sponsorship) per the follow-up plan.