Navacord Action Grant — Application Record

"The Welcome Table" — Holiday-Season Halal Dinner for Calgary Seniors

Complete record of Sahan Heritage Foundation's Navacord Action Grant application — every answer, link, and requirement — ready to submit the moment Federation membership is confirmed.

1. Status & Key Facts

Field

Detail

Status

⏳ READY TO SUBMIT — waiting on Federation membership approval (applied Aug 20, 2026; board meets last Monday of the month)

Funder

Federation of Calgary Communities, sponsored by Navacord

Grant page

https://calgarycommunities.com/navacord-action-grants/

Membership page

https://calgarycommunities.com/become-a-member/

Amount requested

$1,000 (maximum allowed)

Grant type

REIMBURSEMENT — Sahan fronts the money, then is reimbursed against receipts

Application window

Opened Aug 1, 2026 — closes Oct 31, 2026 (only round this year)

Selection

Random draw — no judging; every eligible application has equal chance ($7,000 total pool)

MANDATORY: Awards Night

Thursday, November 26, 2026, 7:00–9:00 pm, in person, venue TBD. A Sahan representative MUST attend or the application is disqualified

If we win — must submit

Photos, short impact story, and receipts

Grant contact

Pooja Shrestha, Community Grant Implementor — pooja@calgarycommunities.com · 403-244-4111 ext. 227

One-per-year rule

Only one Action Grant application per organization per year

2. The Project

"The Welcome Table" — a festive holiday-season dinner where newcomer families, guided by Sahan volunteers, cook and serve a halal dinner for ~70 Calgary seniors who would otherwise spend the season alone. Newcomer youth serve tables; every place setting has a small gift and a printed welcome card connecting guests to community resources (211, library, settlement agencies, Sahan). Pay-it-forward tickets ($10 subsidized / $25 community) — nobody turned away.

Board approval: Resolution passed 5/5 — board is pro-integration with Canadian values.

The story in one line: Newcomers give back to their new country in its season of generosity — integration through contribution, not just adaptation.

Venue — CONFIRMED AND PAID

Field

Detail

Venue

New Indo Canadian Centre (NICC)

Address

Bay 8, 1916A 30th Ave NE, Calgary, AB T2E 7B2

Date

Saturday, December 26, 2026 (rescheduled from July 25, 2026; all other details unchanged)

Cost

$0 — already paid (booked annually; rescheduling confirmed by email)

Venue contact

Jayesh Thacker, Centre Host — info@newicc.org · 403-277-1459 · www.newicc.org

Bookkeeping note

Venue was paid by Sahan in a prior booking cycle — do NOT include venue in Navacord receipts; report as "venue: already covered / in-kind"

Budget — exactly $1,000

Line

Amount

Catered halal dinner + dessert for ~75 people (senior-friendly menu)

$700

Small gift at every place setting + door prizes

$200

Printed welcome cards (community resources, English + Somali)

$100

Venue

$0 (already paid)

All labour

$0 (volunteers)

Total

$1,000

Ticket revenue (if any) is a buffer or seed for the next event — not part of the grant ask.

Practical notes

•	
      Dec 26 = Boxing Day — book the halal caterer EARLY (holiday closures/premiums); confirm NICC kitchen access with Jayesh; confirm volunteer availability for that date

•	
      Recruit seniors via partners: seniors' centres, Meals on Wheels, nearby community associations

•	
      Framing: "the day after the celebrations, when the quiet hits hardest — we set the table"

3. Application Form — Fields & Answers

Form location: "Apply Now" button on https://calgarycommunities.com/navacord-action-grants/

Field

Answer

Organization Name

Sahan Heritage Foundation

Membership checkbox

Check ONLY after membership is confirmed ("Our organization is a member of the Federation of Calgary Communities in good standing")

Contact Person Name

Abdi Obsiye

Contact Person Email

connect@sahanfoundation.ca

Contact Person Phone

5875002073

Photo upload (optional)

A real photo from a past Sahan community event (food/gathering) — authentic beats polished

Checkbox: photos/impact report/receipts

Check (commitment: reimbursement against receipts)

Checkbox: attend in-person awards event

Check (mandatory — Nov 26, 7–9pm)

"Your organization's idea or need (a few sentences)" — paste exactly:

This December, in the season when loneliness hits hardest, Sahan Heritage Foundation will host "The Welcome Table" — a festive holiday-season halal dinner cooked and served by newcomer families for around 70 Calgary seniors who might otherwise spend the season alone. The $1,000 covers the catered meal, dessert, small table gifts, and printed welcome cards connecting guests to community resources like 211. Our venue is donated and every worker is a volunteer. The impact runs both ways: isolated seniors get warmth and company, and newcomer families get the pride of giving back to their new country in its season of generosity.

4. Awards Night — 30-Second Introduction (for whoever attends)

"I'm Abdi from Sahan Heritage Foundation — we're a newcomer-serving society in Calgary. This December 26, our newcomer families are cooking and serving a halal holiday dinner for 70 Calgary seniors who'd otherwise spend the season alone. Newcomers giving back to their new country in its season of generosity. That's what we applied for — and we'd love to meet anyone who wants to be part of it."

5. Timeline

When

Action

Aug 20, 2026

✅ Federation membership application submitted (board meets last Monday of month)

~Aug 31 or Sept 28, 2026

Membership approval expected → pay membership fee

Same day as approval

Submit Navacord application (3 minutes — everything above is ready)

Oct 31, 2026

Application deadline (hard close)

Nov 26, 2026, 7–9pm

AWARDS NIGHT — mandatory attendance (named attendee: ______, backup: ______)

Within 7 days of Awards Night

Winners notified by email

Dec 26, 2026

The Welcome Table dinner at NICC

Early Jan 2027

Submit photos, short impact story, receipts → reimbursement

6. Fallback if we don't win the draw

The dinner still happens: ticket revenue + a small Servus Feel Good Fund or Ward Community Event Fund request can cover ~$1,000. The event's strategic value (a proven pilot before the Good Places decision in mid-December) exists with or without the grant.

7. Registry Details (for reference on any form)

Field

Value

Legal name

Sahan Heritage Foundation

Registered office

66 Redstone Rd NE, Calgary, AB T3N 0M3

Corporate Access Number

5027066496

Business Number (BN)

702217225

Incorporated

April 22, 2025 (Societies Act, Alberta)

Fiscal year end

April 30

Registry email on file

sahanheritage@gmail.com

Application email

connect@sahanfoundation.ca

8. Related Records

•	
      ENMAX sponsorship record: enmax-sponsorship-submission-warm-homes-warm-welcome.md

•	
      Full Good Places project brief: sahan-friday-welcome-nights-good-places-grant.md

•	
      Action plan: what is next.md